## Instructions
Change Readiness Assessment
Enabling the public sector to effectively lead and manage change
Purpose | The Change Readiness Assessment considers the organisational context for a change by assessing the organisation’s change strategy, change approach, and current capability and capacity. Use this tool before commencing a change. It should be completed by a group of leaders, managers or change practitioners.
Step 1 | Establish working group | Establish a working group to complete the change readiness assessment. Aim for diversity of perspectives, by including sponsors, senior leaders, change leads and subject matter experts.
Step 2 | Undertake assessment | Bring the working group together to discuss each assessment question. Consider all perspectives and aim to reach a consensus on ratings. Where consensus cannot be reached, record the lowest rating being considered.
Step 3 | Identify enablers and barriers | Identify areas of strategy, methodology, capability and capacity that will either enable the change or create barriers. Enablers are areas rated at level 4 or 5. These represent strengths that can be leveraged to support the change. Barriers are areas rated at level 1 or 2. These are potential red flags that should be addressed before implementation.
Step 4 | Change Impact Assessment | Once the organisational context has been assessed, it is important to assess the change itself. Consider undertaking a Change Impact Assessment to build a clearer understanding of the change and its impacts.
Step 5 | Develop change strategy | Use the readiness and impact insights to develop an effective change strategy. Consider actions that can be taken in the short term to leverage strengths and address barriers, as well as longer‑term actions to support sustained change.

## Change Readiness Assessment
| Change Readiness Assessment |  | Level 1 Absent | Level 2 Emerging | Level 3 Developing | Level 4 Change ready | Level 5 Change agile | Rating Complete the rating column first. Other fields are calculated automatically. | Enabler Strength to be leveraged Barrier Potential red flag - further consideration needed before proceeding Neutral Neither a strength or barrier
|  |  | Little or no evidence of a change management strategy or methodology; limited or no capability or capacity. Change efforts highly unlikely to succeed. | Some elements of a change management strategy and methodology exist; limited or no capability or capacity. Change efforts unlikely to succeed. | Documented strategy and methodology; emerging / established capability and some capacity to change. Change efforts experience mixed results. | Organisation-wide standards and methodology exist; capability is well-developed; capacity exists to undertake large changes. Change efforts are likely to succeed. | Change strategy and methodology are embedded at all levels of the organisation; highly capable and has capacity to change. Change efforts highly likely to succeed.
| Enabling the public sector to effectively lead and manage change |  | Rating: 19 - 28 | Rating: 29 - 47 | Rating: 48 - 66 | Rating: 67 - 85 | Rating: 86 - 95
Strategy | Strategic importance | Is the leadership of the change defined as a strategic goal, or in your agency’s action plan? | Not defined as a strategic goal or in action plan | Loosely defined as a strategic goal or in action plan | Defined in the agency's action plan | Defined as a strategic goal | Defined as a strategic goal and in the agency's action plan
| Priority level | Is the change acknowledged as a strategic priority by the executive group and by managers / employees? | Not a priority | Low priority | Moderate priority | High priority | Very high priority
| Resourcing levels | Is the strategic importance of the changes you are trying to implement reflected in the availability and investment of resources dedicated to the change effort? | No resources | Some resources | Sufficient resources | Fully resourced | Dedicated CMO
Methodology | Approach | Is there a defined approach to managing the people side of change? | None | Multiple, used infrequently | Multiple, used frequently | Formal, inconsistently applied | Formal and consistently applied
| Standards | Are there defined standards for a consistent approach to leading and managing change? | None | Some standards loosely defined | Most standards defined | Organisation-wide standards | Organisation-wide, industry leading
| Tools | Are tools available to support your change management efforts? | None | Some tools available | Most tools available | All relevant tools available | Comprehensive toolkit
| Application | Are the circumstances in which change management is applied clearly articulated? | When resistance occurs | In response to negative event | At start or before some projects | At start or before most projects | Before all projects
| Practices | Is there consistency or variation in change practices? | No consistency | Some consistency | Moderate consistency | High level of consistency | Uniform approach
| Integration | Is change management integrated into your projects and project management approach? | Not integrated | Some integration | Moderate integration | Integrated at start of projects | Integrated before start of projects
| Communications | How do you intend for employees to find out about changes? | Rumours or gossip | Need to know basis | Informal conversations | Formal conversations | Comprehensive engagement strategy
|  | When do you intend to communicate to employees about the change? | No planned communication | Ad hoc communication | Some planned communication | Regular, consistent communication | Timely, multi-channel communication
Capability | Shared understanding | Is there a shared understanding of the value of change management across the organisation? | No understanding | Low levels of understanding | Moderate levels of understanding | High levels of understanding | Very high levels of understanding
| Training | Is change management training available? | None | Reading materials | Informal training available | Formal training available | Extensive
| Sponsorship | Are change sponsors present and do they participate in the changes? | No sponsors | Some sponsors appointed, little or no presence | Sponsors appointed to all changes, little or no presence | Sponsors appointed and present on all changes | Sponsors appointed, active and visible for all changes
| Competency | Are managers skilled in leading and managing change? | Unskilled | Some skills | Moderate skill levels | Skilled | Highly skilled
|  | Are managers able to coach employees through change? | No coaching ability | Low coaching ability | Moderate coaching ability | Skilled coaches | Expert coaches
Capacity | Change saturation | What level of change saturation is the organisation experiencing? | Very high | High | Moderate | Low | None
| Change fatigue | What level of change fatigue are employees experiencing? | Very high | High | Moderate | Low | None
| Change resistance | What level of resistance is experienced during changes? | Very high | High | Moderate | Low | None
0
Assessment Incomplete
Note on F4: Overall ratings are calculated by summing individual question scores. Rating bands provide an indicative view of overall readiness.
Note on G4: Overall ratings are calculated by summing individual question scores. Rating bands provide an indicative view of overall readiness.
Note on H4: Overall ratings are calculated by summing individual question scores. Rating bands provide an indicative view of overall readiness.
Note on I4: Overall ratings are calculated by summing individual question scores. Rating bands provide an indicative view of overall readiness.
Note on J4: Overall ratings are calculated by summing individual question scores. Rating bands provide an indicative view of overall readiness.
Note on B6: How well the change is aligned to strategic priorities, leadership intent and resourcing.
Note on J8: Change Management Office
Note on B10: How consistently and effectively change management approaches, standards and tools are applied.
Note on B19: The skills, knowledge and behaviours needed to lead and manage change.
Note on B25: The organisation’s current ability to absorb change alongside other priorities.